## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Define negotiation scenarios (Vendor Pricing, Job Offer, Budget Allocation), participant roles, and agent behavioral parameters (Collaborative, Risk-Averse, Aggressive) | Must Have | None | Intern | Completed
Sprint 1 | Sprint 1 | US-02 | Architect overall system flow and interaction modes (Human vs AI and AI vs AI) | Must Have | US-01 | Intern | Completed
Sprint 2 | Sprint 2 | US-03 | Build separate AI agent implementations and stateful orchestrator for turn-by-turn multi-round negotiations | Must Have | US-02 | Intern | Completed
Sprint 2 | Sprint 2 | US-04 | Implement conversation history tracking, context preservation, and duplicate turn processing guards | Must Have | US-03 | Intern | Completed
Sprint 3 | Sprint 3 | US-05 | Construct Negotiation Arena UI with real-time transcript, agent stance indicators, and metrics | Must Have | US-03 | Intern | Completed
Sprint 3 | Sprint 3 | US-06 | Build Human Participant Interface and Deadlock Detection Module for stalled negotiation handling | Should Have | US-04 | Intern | Completed
Sprint 4 | Sprint 4 | US-07 | Implement Outcome Screen displaying final agreement terms, concession timelines, and satisfaction scores | Must Have | US-05 | Intern | Completed
Sprint 4 | Sprint 4 | US-08 | Enable downloadable transcript/summary report generation, end-to-end testing, and project documentation | Should Have | US-07 | Intern | Completed

## Sprint Backlog
Sprint | Task | Start Date | Completion Date | Activity Type | Est. Effort (hrs) | Daily Tracking
Sprint 1 | Define negotiation scenarios and roles (US-01) | Week 1 Day 1 | Week 1 Day 5 | Design | 12 | Completed
Sprint 1 | Architect system flow (US-02) | Week 2 Day 1 | Week 2 Day 5 | Architecture | 10 | Completed
Sprint 2 | Build AI agents and orchestrator (US-03) | Week 3 Day 1 | Week 4 Day 2 | Development | 16 | Completed
Sprint 2 | Implement history tracking and deduplication (US-04) | Week 4 Day 3 | Week 4 Day 5 | Development | 12 | Completed
Sprint 3 | Construct Negotiation Arena UI (US-05) | Week 5 Day 1 | Week 6 Day 1 | UI/UX | 14 | Completed
Sprint 3 | Build Human Participant Interface & Deadlock Module (US-06) | Week 6 Day 2 | Week 6 Day 5 | Development | 12 | Completed
Sprint 4 | Implement Outcome Screen (US-07) | Week 7 Day 1 | Week 7 Day 5 | UI/UX | 10 | Completed
Sprint 4 | Enable reports, testing, and documentation (US-08) | Week 8 Day 1 | Week 8 Day 5 | QA/Docs | 16 | Completed

## Stand-Up Log
Sprint | Impediment | Resolution
Sprint 1 | Differentiating Collaborative, Risk-Averse, and Aggressive agent behavior prompts | Resolved by enforcing strict response constraints and objective boundaries per profile.
Sprint 2 | Early termination after 1 round and double response processing | Resolved by adding context-aware turn tracking and message-id deduplication.
Sprint 3 | UI getting out of sync with backend turn state | Resolved by tying UI state directly to orchestrator response signals.
Sprint 4 | Stale state persisting across new negotiation runs | Resolved by building a state-wipe routine triggered on every new session initialization.

## Retrospectives
Sprint | Start | Stop | Continue | Action Taken
Sprint 1 | Mapping exact prompt boundaries for agent behaviors. | Over-complicating early state schemas. | Documenting edge-case scenario rules explicitly. | Standardized context parameters across all 3 scenarios.
Sprint 2 | Implementing strict turn validation guards. | Allowing non-atomic state updates. | Robust unit testing for multi-turn conversations. | Built deduplication mechanisms to eliminate multi-response bugs.
Sprint 3 | Locking user input during AI processing turns. | Relying on UI-side state alone for turn logic. | Granular logging of deadlock threshold metrics. | Synchronized UI rendering directly with orchestrator state.
Sprint 4 | Session reset on new negotiation start. | Making blocking synchronous API calls for exports. | End-to-end integration testing across all combinations. | Resolved state leakage across sessions and fixed transcript exports.