## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Development Team | 24-Jul-2026 | Scenario selection did not consistently load the correct role and negotiation context. | Milestone 1 | Backend/Frontend Team | Logical | Corrected scenario-to-role mapping and initialized scenario-specific negotiation state. | 25-Jul-2026 | Closed | Verified for Vendor Pricing, Job Offer, and Project Budget.
2 | Development Team | 28-Jul-2026 | Selected Human vs AI mode was not always reflected correctly when starting a new negotiation. | Milestone 1 | Frontend Team | User Interface | Fixed mode-selection state and reset previous negotiation state when a new session starts. | 29-Jul-2026 | Closed | Both Human vs AI and AI vs AI modes verified.
3 | Development Team | 08-Aug-2026 | Agent behavior modes were producing responses that were too similar across Collaborative, Risk-Averse, and Aggressive settings. | Milestone 2 | AI Agent Developer | Logical | Refined behavior instructions and decision constraints so each personality follows a distinct negotiation strategy. | 10-Aug-2026 | Closed | Behavior combinations retested.
4 | Development Team | 12-Aug-2026 | Human-entered negotiation messages were not always being incorporated into the AI's next response context. | Milestone 2 | AI Agent Developer | Logical | Updated context construction to include the current human message, previous offers, roles, objectives, and recent transcript. | 14-Aug-2026 | Closed | Verified across all three scenarios.
5 | Development Team | 21-Aug-2026 | Negotiation sometimes ended after only one round instead of continuing to the next turn. | Milestone 3 | AI Agent Developer | Logical | Fixed turn and round state transitions in the orchestrator and prevented premature completion. | 24-Aug-2026 | Closed | Multi-round Human vs AI and AI vs AI flows verified.
6 | Development Team | 23-Aug-2026 | AI response was occasionally triggered more than once for the same negotiation turn, resulting in repeated transcript messages. | Milestone 3 | AI Agent Developer | Logical | Added per-turn/request identification and duplicate-processing protection while allowing legitimate subsequent turns. | 27-Aug-2026 | Closed | Rapid submission and multi-round tests completed.
7 | Development Team | 26-Aug-2026 | Negotiation transcript did not always update correctly with the latest round and stance information. | Milestone 3 | Frontend Team | User Interface | Corrected transcript state updates and synchronized round/stance metrics with the current negotiation state. | 28-Aug-2026 | Closed | Transcript and metrics verified during multi-round tests.
8 | Development Team | 29-Aug-2026 | Deadlock handling was not triggered reliably when negotiations stalled. | Milestone 3 | AI Agent Developer | Logical | Corrected deadlock round tracking and added a controlled resolution/breakdown transition. | 01-Sep-2026 | Closed | Stalled negotiations now terminate according to the configured condition.
9 | Development Team | 03-Sep-2026 | Final report was not generated after a completed negotiation. | Milestone 4 | Backend Team | Logical | Moved report generation to the final agreement/deadlock completion flow and connected it to the final negotiation state. | 05-Sep-2026 | Closed | Report generation verified after completed negotiations.
10 | Development Team | 05-Sep-2026 | Outcome screen did not consistently display the final agreed terms and round count. | Milestone 4 | Frontend Team | User Interface | Mapped final outcome data to the Outcome Screen and corrected completion-state handling. | 07-Sep-2026 | Closed | Verified with Vendor Pricing and Job Offer scenarios.
11 | Development Team | 07-Sep-2026 | Agreed salary was not consistently displayed after a successful Job Offer negotiation. | Milestone 4 | Backend/Frontend Team | Logical | Persisted agreed salary in the final outcome data and displayed it in the Job Offer outcome section. | 08-Sep-2026 | Closed | Successful salary agreement verified.
12 | Development Team | 09-Sep-2026 | An API request/turn handling error caused an invalid user-turn request during negotiation. | Milestone 4 | Backend Team | Standards | Corrected request construction and turn handling between the frontend, API, orchestrator, and agent layer. | 10-Sep-2026 | Closed | Human and AI turns retested after the correction.
13 | Development Team | 11-Sep-2026 | AI responses were taking longer than expected because of unnecessary processing and repeated calls in some flows. | Milestone 4 | AI Agent Developer | Performance | Removed unnecessary delays and duplicate generation paths; optimized per-turn processing while retaining complete responses. | 13-Sep-2026 | Closed | Response flow retested without line-by-line streaming.
14 | Development Team | 13-Sep-2026 | Downloadable transcript/report output did not always contain the complete final negotiation history. | Milestone 4 | Backend Team | Logical | Updated report/transcript generation to use the final stored negotiation state and complete message history. | 14-Sep-2026 | Closed | Downloaded output checked after agreement and breakdown flows.
15 | Development Team | 15-Sep-2026 | End-to-end validation exposed inconsistent state resets when starting consecutive negotiations. | Milestone 4 | Frontend/Backend Team | Logical | Reset transient negotiation state between sessions while retaining required persistent outcome data. | 16-Sep-2026 | Closed | Final end-to-end regression completed across modes and scenarios.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others
Performance