## UT
Sl: No: | Test Case Name | Test Procedure | Condition to be tested | Expected Result | Actual Result
1 | Project setup and scenario selection [Milestone 1] | Open the application, start a negotiation, and select each available scenario one at a time. Timeline: 23-Jul-2026 to 05-Aug-2026. | Vendor Pricing, Job Offer, and Project Budget scenarios are selectable. | Each scenario loads successfully with its relevant roles and negotiation context. | Pass - all three scenarios load as expected.
2 | Negotiation mode selection [Milestone 1] | Select Human vs AI and AI vs AI modes and start a negotiation. Timeline: 23-Jul-2026 to 05-Aug-2026. | Both supported modes must initialize correctly. | The selected mode starts with the correct participant flow. | Pass - both modes initialize correctly.
3 | Role selection [Milestone 1] | Select valid roles for each scenario and begin the negotiation. Timeline: 23-Jul-2026 to 05-Aug-2026. | Only scenario-relevant roles should be used. | The selected role is assigned to the correct participant and reflected in the negotiation. | Pass - roles are assigned correctly.
4 | Behavior mode configuration [Milestone 2] | Run negotiations using Collaborative, Risk-Averse, and Aggressive behavior settings. Timeline: 06-Aug-2026 to 19-Aug-2026. | Agent behavior must correspond to the selected strategy. | AI responses reflect the configured negotiation behavior. | Pass - behavior modes produce distinct negotiation styles.
5 | Human message submission [Milestone 2] | In Human vs AI mode, enter an offer or response and submit it. Timeline: 06-Aug-2026 to 19-Aug-2026. | A human participant must be able to provide free-text negotiation input. | The message is accepted and appears once in the negotiation transcript. | Pass - human messages are submitted and displayed once.
6 | AI response generation [Milestone 2] | Submit a valid human negotiation message and wait for the AI response. Timeline: 06-Aug-2026 to 19-Aug-2026. | The AI must respond using the current scenario, role, behavior, and conversation context. | One complete AI response is returned and displayed without unnecessary line-by-line streaming. | Pass - complete responses are displayed per turn.
7 | Multi-round context maintenance [Milestone 2] | Continue a Human vs AI negotiation for at least three rounds using changing offers. Timeline: 06-Aug-2026 to 19-Aug-2026. | The AI must retain relevant previous offers and responses. | Each new response reflects the previous negotiation context rather than starting over. | Pass - context is maintained across rounds.
8 | AI vs AI turn orchestration [Milestone 3] | Start an AI vs AI negotiation and observe multiple turns. Timeline: 20-Aug-2026 to 02-Sep-2026. | The orchestrator must alternate the configured agents correctly. | Each agent responds once per turn and the negotiation proceeds to subsequent rounds. | Pass - turns progress correctly across multiple rounds.
9 | Duplicate-response prevention [Milestone 3] | Submit one turn and verify the transcript and backend processing. Timeline: 20-Aug-2026 to 02-Sep-2026. | A single request/turn must not generate or display the same AI response twice. | Exactly one AI response is associated with the processed turn. | Pass - duplicate responses are prevented.
10 | Deadlock detection [Milestone 3] | Run a negotiation with no meaningful progress until the configured deadlock condition is reached. Timeline: 20-Aug-2026 to 02-Sep-2026. | A stalled negotiation must be detected after the configured condition/round threshold. | The system triggers resolution or declares a breakdown instead of continuing indefinitely. | Pass - deadlock handling is triggered at the configured condition.
11 | Agreement detection [Milestone 3] | Conduct a negotiation that reaches mutually accepted terms. Timeline: 20-Aug-2026 to 02-Sep-2026. | A genuine agreement should transition the negotiation to a completed state. | Final agreed terms are captured and the negotiation ends correctly. | Pass - agreement outcome is captured.
12 | Job offer agreed salary [Milestone 3] | Complete a Job Offer negotiation with an agreed salary. Timeline: 20-Aug-2026 to 02-Sep-2026. | The agreed salary must be retained in the final state. | The agreed salary is displayed on the Outcome Screen. | Pass - agreed salary is displayed in the outcome.
13 | Outcome screen [Milestone 4] | Complete an agreement or deadlock and open the Outcome Screen. Timeline: 03-Sep-2026 to 16-Sep-2026. | Final outcome data must be available after negotiation completion. | Final terms/status, concession timeline, rounds elapsed, and objective satisfaction scores are displayed. | Pass - outcome information is displayed.
14 | Download transcript and report [Milestone 4] | Complete a negotiation and use the download/report controls. Timeline: 03-Sep-2026 to 16-Sep-2026. | The completed negotiation must produce downloadable output. | Transcript and summary report are generated with the completed negotiation data. | Pass - downloadable transcript/report functionality is available.
15 | End-to-end scenario and personality testing [Milestone 4] | Run both modes across all three scenarios using different behavior combinations. Timeline: 03-Sep-2026 to 16-Sep-2026. | The complete application flow must work across supported combinations. | Negotiations complete or deadlock correctly without breaking transcript, outcome, or report generation. | Pass - end-to-end flows validated across modes, scenarios, and behavior combinations.

## Milestone Timeline
Milestone | Duration | Dates | Main Focus
Milestone 1 | 2 weeks | 23-Jul-2026 to 05-Aug-2026 | Core project setup, scenarios, modes, and role flow
Milestone 2 | 2 weeks | 06-Aug-2026 to 19-Aug-2026 | Agent behavior and Human Participant interaction
Milestone 3 | 2 weeks | 20-Aug-2026 to 02-Sep-2026 | Negotiation Arena, multi-round flow, deadlock handling, validation
Milestone 4 | 2 weeks | 03-Sep-2026 to 16-Sep-2026 | Outcome screen, reports, end-to-end testing, documentation, final demo